## Slide 2: Planning and scheduling your thesis
Steven Lecompte
department of electromechanical, systems and metal engineering
  research group sustainable thermo-fluid energy systems

## Slide 3: Why make a Planning?
October | November | December | January
February | March | April | May
What can I do?
To own your project!
Notes: Core message: make a planning to own your project:
ownership = you are responsible for the project’s results and timing
Owning your timing will bring peace to your master thesis.
TODAY: a basic framework for project planning + a basic tool for project planning.

## Slide 4: Project definition
Question
Answer
Process
Time
Quality
Budget

## Slide 5: Phasing your master thesis
After each phase build in:
  Concrete result
  Decision moment
Control the scope of the project
Idea
Result
Analyze
Prepare
Execute
Closure
Why?
What?
How?
As planned?
Ok?

## Slide 6: Phasing your master thesis
We want to reduce the cost of our fire tube boilers
Idea
Analyze
Prepare
Execute
Closure
Why?: because we want to increase revenue
What? Customize to the need of the specific client.
How? Build a heat transfer / design model of the boiler.
As planned?
Our designs are not tailor made for each customer -> oversiz
Can we use the models for boiler design?

## Slide 7: How to do a large task?
How to eat an elephant ?

## Slide 8: Work breakdown structure
Supervisor
Technician
Divide the project into sub tasks until:
  Each task has one owner
  Each task has an estimated duration
Identify milestones
  e.g. literature review, finished setup …
Identify decision moments
  e.g. components to buy , scope of the study
Identify logical sequence of tasks

## Slide 9: Task duration
Large tasks are hard to estimate
Subdivide a task until you can estimate the task duration
e.g. : How long does it take to cook beef stew?
Cutting onions 10 min
Cutting meat 10 min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Stewing 1,5 h
=> 2h15 min ?

## Slide 10: Milestones and decision moments
e.g. : beef stew?
Milestone: Mise en place
Milestone: beefstew
Decision moment: tasting
Cutting onions 10 min
Cutting meat 10 min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Stewing 1,5 h

## Slide 11: Task ownership
e.g. : beef stew?
Milestone: Mise en place
Milestone: beefstew
Decision moment: tasting
Cutting onions 10 min
Cutting meat 10 min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Stewing 1,5 h
Does it still take 2h15min?

## Slide 12: Network planning
Cutting onions 10 min
Cutting meat 10 min
Stewing 1,5 h
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Taste?


Beef stew

## Slide 13: Critical Path
=The longest chain of dependent tasks
  Any delay in the critical path is a delay in the project
Cutting onions 10 min
Cutting meat 10 min
Stewing 1,5 h
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Taste?


Beef stew
Path 1: 1h55

## Slide 14: Critical Path
=The longest chain of dependent tasks
  Any delay in the critical path is a delay in the project
Cutting onions 10 min
Cutting meat 10 min
Stewing 1,5 h min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Taste?


Beef stew
Path 1: 1h55
Path 2: 1h45

## Slide 15: Critical Path
=The longest chain of dependent tasks
  Any delay in the critical path is a delay in the project
Cutting onions 10 min
Cutting meat 10 min
Stewing 1,5 h min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Taste?


Beef stew
Path 1: 1h55
Path 2: 1h45
Path 3: 1h45

## Slide 16: Critical Path
=The longest chain of dependent tasks
  Any delay in the critical path is a delay in the project
Cutting onions 10 min
Cutting meat 10 min
Stewing 1,5 h min
Collecting herbs 15 min
Cooking onions 10 min
Searing meat 5 min
Taste?


Beef stew
Path 1: 1h55
Path 2: 1h45
Path 3: 1h45
Critical path

## Slide 17: Gantt chart
= Graphical overview of:
Tasks
Sequence
Milestones
Task name | 0 | 10min | 20min |  | 30min | 40min | 50min | 1h | 1h 10 | 1h 20 | 1h 30 | 1h 40 | 1h 50 | 
Cutting onions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cooking onions |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Cutting meat |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Herbs |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Searing |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stewing |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Tasting? |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Decision
moments
Notes: What is a gantt chart?
- task
- duration
- sequence +
possibly:
milestones or deliverables
How to use:
keep track of your progress vs planned progress
adjust your planning and goals along the way

## Slide 18: Project planning example: garden shed
This holiday you will build a garden shed in your new garden. You already know the size and location of the shed (4x5m). Furthermore, the required installations are also known: 3 single phase electricity connections, tap water and rainwater connection and finally lighting. The precise design of the shed is still to be determined.
The shed first requires the vegetation to be cleared. After this first step, the foundation for the base plate is dug using a rental machine. Concrete has to be ordered and poured in the foundation. The concrete base plate should contain steel supports at the location of the main supporting pillars which should follow from finishing the design of the shed.
Based on the design, beams of wood, windows and doors are ordered. The structure is built after which the electrical and water connections are finished. For the electrical and water connections, a ditch is dug from the main house to the garden shed. Finally, the work bench and tools are placed in the shed.

## Slide 19: garden shed: Step 1 Task list
Design shed
Clear vegetations
Order-deliver excavator
Order-deliver concrete
Pour base plate
Order wood windows and doors
Electrical and water connections
Dig ditch
Place the work bench
Construct shed

## Slide 20: garden shed: Step 2 network planning
Design shed
Clear vegetation
Order-deliver excavator
Order-deliver concrete
Pour base plate
Order wood windows and doors
Electrical and water connections
Dig ditch
Place the work bench
Construct shed
Dig foundation
Work breakdown structure

## Slide 21: garden shed: Step 3: task duration
Design shed
Order-deliver excavator
Order-deliver concrete
Pour base plate
Order wood windows and doors
Electrical and water connections
Dig ditch
Place the work bench
Construct shed
Dig foundation
Clear vegetation
5d
2d
3w
2w
5d
4w
4w
Early start | Duration | Early Finish
Task name |  | 
Late start | Slack | Late Finish
2d
1d
1d
0,5d

## Slide 22: garden shed: Step 3: Critical path
Design shed
Order-deliver excavator
Order-deliver concrete
Pour base plate
Order wood windows and doors
Electrical and water connections
Dig ditch
Place the work bench
Construct shed
Dig foundation
Clear vegetation
5d
2d
3w
2w
5d
4w
4w
Early start | Duration | Early Finish
Task name |  | 
Late start | Slack | Late Finish
2d
1d
1d
0,5d
0d
0d
3w
0d
0d
3w2
5d
1week=5days
5w
3w
5d
2w
5d
3w2
3w3
5w
9w
0d
2d
9w
9w
9w,5
9w1

## Slide 23: garden shed: Step 3: critical path
Design shed
Order-deliver excavator
Order-deliver concrete
Pour base plate
Order wood windows and doors
Electrical and water connections
Dig ditch
Place the work bench
Construct shed
Dig foundation
Clear vegetation
5d
2d
3w
2w
5d
4w
4w
Early start | Duration | Early Finish
Task name |  | 
Late start | Slack | Late Finish
2d
1d
1d
0,5d
0d
0d
3w
0d
0d
3w2
5d
1week=5days
5w
3w
5d
2w
5d
3w2
3w3
5w
9w
0d
2d
9w
9w
9w,5
9w1
9w1
9w
5w
5d
9w
5w
5d
0d
0d
0d
0d
0d
9w
9w1
8w3
9w,5
,5d
8w3
5w
4w4
1w2
4w4
2w4
2w4
4w4
1w2
4w2
4w2
1w2
1w2
4w2
3w2
3w2

## Slide 24: garden shed: Step 3: Gant chart

## Slide 25: Case study: my master thesis
We want to reduce the cost of our fire tube boilers.
Notes: Project planning: can be quite abstract
Therefore: use an example to show the implementation of a planning
Present example: my master thesis.
Core message : Deconinck Wanson wanted to reduce the cost of their fire tube boiler. Before the master thesis they used catalogue solutions based on their experience.
They wanted to model the FTB to tailor each boiler to the needs of a specific client.
The result would be a downsized design == cheaper boiler.

## Slide 26: Work breakdown structure: case
Prepare
Literature review
Experimental boiler Data: 1
Summary of available articles: 5 days
Read selected articles: 20 days
Write review story: 3 days
Table of articles
Content review
Model structure
Summarize read articles: 5 days
Steady state data
Select articles

## Slide 27: Work breakdown structure: case
27
Program model
Furnace: 5 days
Turn box: 1 day
Execute
Test
models
Verification
Validation 4
Tube pass: 5 days
Integration: 10 day
Furnace: 2
Turn box: 2
Tube pass: 2
Integration: 2
Design analysis: 10
Content: model structure
Content: Verification
Content: validation
Content: guide

## Slide 28: Work breakdown structure: case
Closure
Dissertation
Presentation: 5
Book
Literature review: 10 days
Chapter model structure: 5 days
Chapter verification and validation: 5 days
Chapter: design analysis: 10 days
Extended abstract: 5 days
Summary: 1 day

## Slide 29: Network planning
Identify the logical sequence of tasks
Based on dependencies :
- task-intrinsic
- resource bound
Summary of available articles
Read selected articles
Write review
Summarize read articles
Select articles
Be on holiday

## Slide 30: Critical path
=The longest chain of dependent tasks
  Any delay in the critical path is a delay in the project
Summary of available articles: 5
Read selected articles:
20
Write review story:
3
Summarize read articles:
5
Path length: 33 days
Model structure
Program model: 21
Test models: 14
Design analysis: 10
Path length: 75 days => critical path

## Slide 31
 |  |  |  | week |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Literature review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1.1 | Summary of available articles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1.2 | Read selected articles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1.3 | Summarize read articles |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1.4 | Write review story |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2 | Experimental boiler data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3 | Program model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.1 |  | Furnace |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.2 |  | Tube pass |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.3 |  | turn box |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 3.4 |  | integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
4 | Test models |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 4.1 |  | verification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 4.1.1 |  | Furnace |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 4.1.2 |  | Tube pass |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 4.1.3 |  | Turn box |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  | 4.1.4 |  | Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 4.2 |  | validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 | Design analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Notes: Example for the present case:
From WBS->network -> critical path->

## Slide 32: Summary
Project phasing
Work Breakdown structure
Network planning
Identify critical path
Scheduling: Gantt chart
Divide and conquer
Identify logical task sequence
Find path with longest duration
Ownership and duration
When will I do what
Notes: Use stick ons

## Slide 33: Some final advise
Planning is a tool, not a goal
Include contingency in your planning
Start roughly, refine as you come closer
The worst plan is no plan at all
  The second worst plan is a plan that cannot change

## Slide 34: Steven Lecompte Department of electromechanical, systems and metal engineering E wim.beyne@ugent.be www.ugent.be
Universiteit Gent